## Slide 1: Dependent Audit

## Slide 2: Dependent Audit Overview
In response to findings in the FY14 Health Benefits Performance Audit (Report No. 2014-02), the Human Resources Department is actively reviewing employee files with covered dependents.

## Slide 3: Dependent Audit Goal
To increase the number of employee and retiree dependent verification compliance from 61% (audit performed by Segal Consulting in August 2017) to 92.5%. Segal Consulting sampled 228 dependent files and 61% had supporting documentation for each covered dependent.

## Slide 4: Dependent Verification – Current State
Employee enrolls and selects dependent coverage
Supporting documentation is submitted within 30 days
Payroll deduction begins (even if dependents have not been verified)

## Slide 5: Dependent Verification – Future State
Employee enrolls and selects dependent coverage
Supporting documentation is submitted within 30 days
Verification of supporting documentation
Payroll deductions begins

## Slide 6: Stage One
Process Gap Analysis
Assessed and revised current process for risk.
Defined verification requirements.
Created communication plan.
Completed February 22, 2018

## Slide 7: Stage Two
Communication and File Remediation
Participants receive a letter announcing the beginning of the audit and deadline.
Participants submit dependent verification documentation.
Four phases of completion

## Slide 8: Stage Two: Phase One
Grandchildren
Reviewed 350 dependent files
  180 dependents verified
  170 dependents termed
Completed September 21, 2018

## Slide 9: Future Phases
Phase 2: Open Access Plan
  3,236 dependent files
Phase 3: Consumer Driven Health Plan
  2,342 dependent files
Phase 4: Limited Plan
  20,505 dependent files