## Slide 1: Disaster Recovery & Consulting Services Update
City of Houston
June 30, 2020

## Slide 2: Contract Summary
Key Activities | 
RFP Issued | April 2016
Contract Awarded | February 2017 ($5M)
Contract Amendment | December 2017 ($32M)
Total Contract Award | $37M
Contract Term (3 years plus two 1 year renewals) | February 2017 – February 2022
Spend to Date | $30M
Harvey Monthly Spend | $866K*
MWBE Goal | 24%
Current MWBE Participation | 19%
Harvey
*Does not include COVID-19 ramp up
1

## Slide 3: Hurricane Harvey Program Support
The City is moving sharply into Long Term Infrastructure Recovery entering Year 3 after the disaster.
2

## Slide 4: Hurricane Harvey FEMA Programs Program through Project Management

## Slide 5: Funding Flow and Federal/State Engagements

## Slide 6: Hurricane Harvey FEMA Public Assistance Reimbursement Model for Rebuilding and Mitigation

## Slide 7: Hurricane Harvey Program Status On Pace in Year 3 of 10 Year Recovery Program
Chart: 
| Category A - Debris Removal - Solid Waste | Category B -Emergency Work - GSD, HPD, HFD, HPW, HFC | Category C - Roads and Bridges - HPARD | Category D - Water Control Facilites - HPW | Category E - Buildings and Equipment - GSD, HFC, HPW, FMD | Category F - Utilities - HPW | Category G - Parks, Recreational Facilities, and Other - HFC, HPARD
 | 0.97 | 0.9 | 0.5 | 0.02 | 0.05 | 0.02 | 0.59
97%

## Slide 8: Delivering on our 5 Commitments to the City
Processing $350M in Harvey response costs to FEMA in Year 1
Conducting more than 500 Damage Assessments in Year 1
Processing total of $564.9M in Harvey costs over 3 years
Conducted 547 Assessments and Inspections over two years
Tetra Tech has partnered with the City to meet or exceed established by Mayor and Council in 2017.
2017
Today

## Slide 9: Delivering on our 5 Commitments to the City
Identifying both visible and hidden damage from Harvey
Commitment to build it back better wherever possible
Documented 31% additional damages in facilities vs. FEMA
Working with FEMA and State on $320.36M of Resilience funding
Billions of dollars in damages to City infrastructure available for federal assistance
Validating estimated $2.2B in rebuilding and mitigation from FEMA programs
2017
Today

## Slide 10: Program Accomplishments to Date Key Metrics
Financial
Program/Policy
Mitigation
City Department Support

## Slide 11: Program Accomplishments to Date
Financial
#1 in State of Texas for FEMA Recovery Dollars Obligated by FEMA for local governments
Received funding for $292.7M of the $365.9M currently obligated by FEMA back to the City for Harvey Repairs.
Leveraged new FEMA program to recover Tetra Tech costs at 100% federal funding
Maximized insurance proceeds of $102.6M for flood loss, wind and business interruption
Category | $ Received (in Millions)
A (Debris) | 83.9
B (Emergency Work) | 123.3
E (Bldgs & Equip) | 32.7
G (Parks, Rec./Fac.) | 29.9
Z (MCIP) | 16.0
SB 7 (Local Share) | 6.9
Total | $292.7

## Slide 12: Program Accomplishments to Date
3
Worked collaboratively with Finance Department to maximize fiscal resources for ongoing disaster recovery through internal controls and audits
Partnered with SPD on proactive and preventative processes based on federal guidelines for 100+ Harvey-related procurements ensuring dollars remain in City
Assisted Houston First Corporation to expedite receiving funds from FEMA and State within 2 years and targeted for closeout in 2020
Inspector General Review on Procurements resulted in zero findings due to processes put in place
City Department Support
Under new FEMA policy, a 3-year timeline limiting “clawback” begins once a project is closed out by the City.

## Slide 13: Program Accomplishments to Date
56
COH Finance led collaborative approach to disaster– “Strike Team”, Denton/Austin In-Person Meetings, Weekly “Ball-in-Court” working sessions
Received approval from FEMA on apportionment and allocation methodology within 1 year for insurance proceeds
Supported Chief Recovery Officer during legislative session on SB7 to save the City an estimated $24.8M to date.
Program/Policy
The City led process to improve FEMA’s online tool (GrantsPortal) resulting in 18 changes in the system
FEMA is 52% complete with adopting 56 distinct policy changes from the DRRA that impact Harvey recovery.

## Slide 14: Program Accomplishments to Date
1:7
Obtained $14.2 in federal funds for Phase 1 Hazard Mitigation – Infrastructure
Obtained $17.4 in federal funds for Flood Mitigation - Residential
On pace to bring in an additional $0.69 in hazard mitigation funding for every $1 spent on repair for City projects.
Mitigation
Awarded $14.8M in federal funds for Phase 1 Hazard Mitigation – Infrastructure (HMGP)
Awarded $38.9M in federal funds for Flood Mitigation – Residential (FMA) for ‘19 & ’20.
Working with FEMA to develop 178 additional mitigation proposals for City facilities.
FEMA states that for every $1 spent on mitigation, you will save $7 in future repair costs from disasters.

## Slide 15: Projected Milestones for 2020/2021
Milestones | Deadline | Status
Awarded $9.4M from State for Local Cost Share Assistance (SB7) | June 2020 | Completed
FEMA Approved new $21.5M in Flood Mitigation | June 2020 | In Process
Receive $4.5M for TIRZ 17 HMGP Application – Phase 1 | July 2020 | On Pace
Receive additional $24M for 406 Mitigation | Aug 2020 | On Pace
Receive $13M from State for closeout retainage currently held by State | Nov 2020 | On Pace
Updating FEMA GrantsPortal from supplemental damage assessments for HPW | Feb 2021 | On Pace
New Obligation of Projects at $1.3B | Feb 2021 | On Pace
Reimbursements of $800M (in General/Enterprise Funds) | Feb 2021 | On Pace
Receive approval for additional $266M for HMGP – Phase 2 | May 2021 | On Pace

## Slide 16: Increase Contract Cap Request:
Breakdown:
  Harvey: $10M
  COVID-19 Request:
    FEMA Public Assistance $1M
    Coronavirus Relief Fund $5M
  Total COVID-19 $ 6M
  Other(s)/Future Disaster(s) $ 5M
Total Increase $21M

## Slide 17: Program Operations: Actual Allocation
Scope Area | Cost (M) June 2020* | Initial (%) | Cost (M) Thru Feb 2022 | Cumulative (%)
Damage Assessments | $14.5 | 39% | $1.95 | 28%
Project Development | $18.1 | 49% | $11.7 | 51%
Grant Administration | $4.2 | 11% | $4.43 | 15%
Closeout | $0.2 | 1% | $1.95 | 4%
Audit | $ - | 0% | $.97 | 2%
Total | $37 | 100% | $21 | 100%
Current Estimates
*Expected for the period from August 2017 - October 2020
Estimate for Future Years**
**Expected for the period of September 2020 through February 2022

## Slide 18: COVID-19 Program Support
17
COVID-19 is an unprecedented disaster for the City of Houston and the Nation.

## Slide 19: COVID-19 Activities – March Thru December 2020
Tetra Tech’s Role:
Documentation and Procurement Compliance Analysis
Compliance Training
Daily Advisory Consulting Services
Data Management/Records Retention
Audit preparation and support
FEMA PA Project Formulation for Claims Submission
Duplication of Benefits Assessments
Key Issues and Considerations:
Adherence 2 CFR 200 Compliance
Preparation for OIG and other Audits
Must Spend by December 30, 2020
Evolving federal regulations
Disaster unlike any in history
Medical Expenses
Public Health Expenses
Payroll Expenses
Expenses to Facilitate Compliance
Economic Assistance
Administrative Expenses

## Slide 20: Questions and Discussion